SCRUB — TEAM ORGANISATION & 1-MONTH EXECUTION PLAN

Organisational Structure · Roles · Week-by-Week Task Plan · Meeting Cadence · KPIs

AASK Technologies  ·  RV College of Engineering, Bengaluru  ·  May – June 2026

Team: 11 Members  ·  Project Lead: Krishna Purwar

FINAL DELIVERABLE:  Industry-grade SCRUB prototype ready for investor demonstration + 3,500+ community (Instagram, LinkedIn, Reddit)  —  in 30 days.

1.  TEAM ROSTER & ROLE ASSIGNMENTS

| # | Name | Roll No. | Dept | Team Role | Reporting To |
| --- | --- | --- | --- | --- | --- |
| 00 | Krishna Purwar | Project Lead | ME — RVCE | FOUNDER / PROJECT LEAD | Faculty Mentors |
| 01 | Hariharan | 1RV24ME043 | ME | Mechanical Lead | Krishna |
| 02 | Skanda S.B. | 1RV24ME104 | ME | Mechanical — Fabrication | Hariharan |
| 03 | Siddiq | 1RV24ME103 | ME | Mechanical — CAD & FEA | Hariharan |
| 04 | Ashutosh | 1RV24EC039 | ECE | Electronics Lead | Krishna |
| 05 | Varshaa Pradeep | 1RV24EE058 | ECE | Hardware — Sensors & PCB | Ashutosh |
| 06 | Lakshya Utradhi | 1RV24EE025 | ECE | Hardware — Power & BMS | Ashutosh |
| 07 | Adya Dalmia | 1RV24CS020 | CSE | Software Lead | Krishna |
| 08 | Suraj Gupta | 1RV24CS291 | CSE | Software — AI/ML | Adya |
| 09 | Dishita | 1RV24CS079 | CSE | Software — Navigation | Adya |
| 10 | Syed Farhan | 1RV25CS184 | CSE | Software — Dashboard/IoT | Adya |
| 11 | Prasanna Roy | 1RV25CS120 | MARKET | Growth & Media Lead | Krishna |

⚠  Every team member must sign the NDA + IP Assignment Agreement before starting. No exceptions. IP filing 2 (weed-puller) must be submitted BEFORE any public demo of the mechanism.

2.  ORGANISATIONAL STRUCTURE

The team operates in a flat-hierarchy with domain leads. Each domain lead owns their track end-to-end and reports daily to Krishna. Cross-domain collaboration is mandatory — mechanical needs electronics for motor specs, electronics needs software for firmware, software needs mechanical for integration specs.

ORGANISATIONAL CHART

KRISHNA PURWAR  —  PROJECT LEAD & FOUNDER

│

├──────────────────┬──────────────────┬──────────────────┤

| 🔧 MECHANICAL Lead: Hariharan Skanda · Siddiq | ⚡ ELECTRONICS Lead: Ashutosh Varshaa · Lakshya | 💻 SOFTWARE Lead: Adya Suraj · Dishita · Farhan | 📣 GROWTH Lead: Prasanna (+ future recruit) |
| --- | --- | --- | --- |

→  Cross-domain integration pair: Ashutosh (Electronics Lead) has a standing sync with Adya (Software Lead) every Tuesday and Thursday at 9 PM to align on PCB pin-outs, firmware interfaces, and sensor data formats.

3.  INDIVIDUAL ROLE SPECIFICATIONS

3.1  Mechanical Engineering Team

Hariharan  ·  Mechanical Lead  —  ME — 1RV24ME043

Primary ownership: All fabrication, vendor coordination, and mechanical integration. Hariharan is accountable for the physical robot being field-ready by end of Week 4.

- Week 1: Print and assemble mesh tensioner components (IN PROGRESS). Finalise material order for side panels (fibreglass). Order EVA foam for drive roller grip layer.

- Week 2: Fabricate and fit triangular side containment panels. Install mesh liner sheet. Test drive roller grip wrap — re-check tensioner post-installation.

- Week 3: Finalize propeller replacement — add screw-mount slots to CAD, print propeller guard/shroud (PETG/ASA). Assemble and test on water.

- Week 4: Full mechanical integration test with electronics installed. Waterproofing pass. Pre-demo inspection checklist signed off.

- Documentation: Maintain design log after every fabrication decision. All vendor orders in writing (WhatsApp with drawing attached — never verbal).

Skanda Seetharaman B.  ·  Mechanical — Fabrication  —  ME — 1RV24ME104

- Week 1: 3D print tensioner saddle clamp body (lower half + upper clamp), lateral rod end-brackets ×2. Assemble tensioner on chassis.

- Week 2: Cut and fit fibreglass triangular side containment panels (both sides). Install liner sheet between mesh runs. Run lateral slip test — with and without anti-slip disks.

- Week 3: Physical assembly of propeller guard shroud. Fabricate cable management clips and wire routing brackets for electronics enclosure.

- Week 4: Prototype 2 full assembly alongside Hariharan. Pool/water body integration test. Photograph every stage for content library.

Siddiq  ·  Mechanical — CAD & FEA  —  ME — 1RV24ME103

- Week 1: Complete as-built SolidWorks model of current prototype v0.6 — hull, conveyor assembly, all mounted components. Upload to shared drive.

- Week 2: Run FEA (SolidWorks Simulation): static structural at 75 kg load + buoyancy loads. Document safety factors. Begin CAD of conveyor upgrades.

- Week 3: Complete detailed CAD of propeller guard/shroud (snap-fit, PETG). CAD of electronics enclosure (IP54 gasketed lid). Submit to Skanda for printing.

- Week 4: Generate full manufacturing drawings with tolerances for IP filing support. Begin v2.0 concept sketches — weed-puller mechanism (3 concepts for IP Filing 2 brief).

3.2  Electronics & Electrical Team

Ashutosh  ·  Electronics Lead  —  ECE — 1RV24EC039

Primary ownership: All PCB design, electronics integration, power system, and embedded firmware. Ashutosh is accountable for zero electronics failure during Week 4 water test.

- Week 1: KiCad PCB v2 schematic — motor control, sensor integration, power rails (48V→12V→5V→3.3V). Submit Gerbers to Lion Circuits by Day 5.

- Week 2: PCB v2 arrives — assemble, solder, bench test ALL circuits on lab power supply before integration. Write STM32 motor PWM firmware (20 kHz).

- Week 3: Integrate PCB v2 into robot chassis. Run sensor validation against lab standards (pH, turbidity, TDS). Verify BMS protection thresholds.

- Week 4: PCB v2 waterproofing — conformal coat (MG Chemicals 422B). IP65 enclosure fitting. 1-hour stress test in waterproof enclosure before pool test.

- Cross-domain sync: Tuesday + Thursday 9 PM with Adya — align on UART protocol, STM32↔RPi5 message format, sensor pin assignments.

Varshaa Pradeep  ·  Hardware — Sensors & PCB  —  ECE — 1RV24EE058

- Week 1: Bench calibration of all sensors: pH (2-point buffer calibration), turbidity (NTU standard), TDS, temperature. Document calibration coefficients.

- Week 2: PCB assembly support — SMD soldering, sensor breakout connections. Log all readings in shared test sheet. Cross-validate pH + turbidity vs. lab standard.

- Week 3: Wire harness fabrication — marine-grade tinned copper, colour-coded, labelled. Install GPS (NEO-M8N) with clear sky-view on mast. Verify NMEA data stream.

- Week 4: Full sensor suite live test in water body — log all parameters at 1 Hz for 30 minutes. Export CSV. Share with Farhan for dashboard display.

Lakshya Utradhi  ·  Hardware — Power & BMS  —  ECE — 1RV24EE025

- Week 1: Assemble 16S LiFePO₄ battery pack — cell matching, series connection, insulation tape. Connect Daly BMS. Verify OVP/UVP thresholds with lab meter.

- Week 2: Install and test DC-DC converters: 48V→12V (Meanwell SD-25D-12), 48V→5V (PD trigger). Verify all rail voltages under load. Document current draw per rail.

- Week 3: Install MPPT charge controller (Victron 75/15). Test solar panel → battery charging cycle. Verify boost operation (19.5V panel → 51.2V bus). Log charging data.

- Week 4: Fuse sizing and installation (ANL 15A main, blade fuses per branch). Full power system load test: all subsystems on simultaneously for 60 minutes. Record temperature of BMS and converters.

3.3  Software Team

Adya Dalmia  ·  Software Lead  —  CSE — 1RV24CS020

Primary ownership: Entire software stack — ML model, navigation, dashboard, IoT. Adya reviews all code before merge. No code goes to the robot without lead sign-off.

- Week 1: Set up GitHub (private repo) — branch strategy: main/dev/feature. RPi5 Ubuntu 22.04 setup. Define UART protocol spec for RPi5↔STM32. Code review framework.

- Week 2: YOLOv8 model retraining on SCRUB lake dataset. Achieve ≥90% mAP on test set. Version tag model weights. Write inference + NMS pipeline.

- Week 3: Integrate navigation + ML + IoT into single unified process on RPi5. End-to-end test: GPS waypoint → debris detect → conveyor trigger → return. Record demo video.

- Week 4: Software freeze. v1.0 tag on GitHub. Write README + API docs. Prepare demo mode (one-click launch, pre-loaded Kengeri waypoints). Code handoff package.

Suraj Gupta  ·  Software — AI/ML  —  CSE — 1RV24CS291

- Week 1: Collect and organise SCRUB lake dataset — label floating plastic, thermocol, organic matter, clear water (use Roboflow). Target: 500+ annotated frames.

- Week 2: Train YOLOv8n on dataset. Evaluate: mAP, precision, recall, confusion matrix. Iterate augmentation (brightness, contrast, hue — lake-specific). Export TFLite weights.

- Week 3: Deploy TFLite model on RPi5. Benchmark: frames per second, CPU/RAM usage. Optimise if <10 FPS. Write detection → navigation trigger callback.

- Week 4: Test model on live video at pool/water body. Log false positives (reeds, reflections). Document and tag v1.0 model. Write model card for IP Filing 3 support.

Dishita  ·  Software — Navigation  —  CSE — 1RV24CS079

- Week 1: Implement GPS boustrophedon (lawn-mower) path planner in Python. Simulate on Kengeri Lake polygon (GeoJSON). Unit test with mock GPS feed.

- Week 2: Integrate obstacle avoidance: HC-SR04 → STM32 UART → RPi5 halt command. Bench test: robot halts within 20 cm of obstacle in 3/3 trials.

- Week 3: Dead-reckoning fallback: IMU (MPU6050) + wheel encoder odometry for GPS dropout. Kalman filter fusion. Test 30s GPS-off → re-acquire scenario.

- Week 4: Full autonomous run test: launch → grid path → debris collect → return to dock. Record GPS track overlay. Export clean demo video for Growth team.

Syed Farhan Hashmi  ·  Software — Dashboard & IoT  —  CSE — 1RV25CS184

- Week 1: Dashboard v2 backend: FastAPI + MQTT broker. Define all data topics: GPS, pH, turbidity, DO, TDS, speed, bin-fill, video stream endpoint.

- Week 2: Frontend: live GPS map (Leaflet.js), real-time sensor charts (Chart.js), live video embed, threshold alert popups. Deploy on public URL (Render/Railway).

- Week 3: Offline buffer: SQLite local storage on RPi5, retry queue for 4G drops. Test: cut internet for 10 min → data queued → reconnect → all data uploaded.

- Week 4: Dashboard demo mode: show Kengeri Lake test data replay. Record 60-second screen capture for investor pitch. Write 1-page dashboard user guide.

3.4  Growth & Media

Prasanna Roy  ·  Growth & Media Lead  —  MARKET — 1RV25CS120

PRIMARY KPI: 3,500+ total community by Day 30  (Instagram 2,000 + LinkedIn 900 + Reddit 400 + Email 200).  This is non-negotiable. Every piece of engineering output must be turned into content within 48 hours.

- Week 1: Set up all platforms (@aask.tech / @scrub.robot). Content calendar (Notion). Edit 3 reels from existing Kengeri footage. Post intro reel Day 1. Write founder story post for LinkedIn.

- Week 2: Email United Way Bengaluru, KSPCB, Infosys Foundation. 'Build in public' posts: fabrication updates, sensor data, PCB photos. Post 5× per week. Start Reddit presence (r/robotics, r/IndiaStartups, r/bangalore).

- Week 3: Field trial reel (SCRUB on water) — this is the biggest content piece. Post same day as trial. 'IP filed' announcement post. YouTube: 3-minute build documentary. Reach 1,500 IG followers by end of Week 3.

- Week 4: Demo Day announcement campaign (3 posts build-up). Investor reel (90-sec cinematic). YourStory / Inc42 story submission. Final community count screenshot as KPI proof. Thank-you post after Demo Day.

- Reddit strategy: Post 1x/week to r/robotics, r/IndiaStartups, r/bangalore, r/MachineLearning with genuine value-add (lake data, build photos, technical questions). No spam — engagement only.

4.  MEETING STRUCTURE & OPERATING RHYTHM

| Meeting | Type | Who | Time | Duration | Output |
| --- | --- | --- | --- | --- | --- |
| Daily Standup | Online (daily) | All 11 members | 9:00 PM IST | 15 min | Each person: Done yesterday / Doing today / Any blocker. Blockers resolved same day. |
| Cross-Domain Sync | Online (Tue+Thu) | Ashutosh + Adya | 9:30 PM IST | 20 min | Firmware/software interface alignment: pin assignments, UART spec, timing. |
| Weekly Review | Offline (Saturday) | All 11 members | 10:00 AM IST | 90 min | Demo of week's work (live, not slides). Milestone check. Next week sprint planning. |
| 1:1 Lead Check-in | Online (Wed) | Krishna + each lead | Rolling, 15 min each | 15 min ea. | Blockers, resource needs, cross-team dependencies. Leads only. |
| Content Review | Online (Friday) | Prasanna + Krishna | 8:00 PM IST | 20 min | Review all content before posting. Approve or revise. Next week's calendar confirmed. |
| Demo Day Prep | Offline (Day 28) | All 11 | Full day | 8 hours | Full system integration run. Investor reel shoot. Final QA checklist. |

→  Daily standup is 15 minutes MAXIMUM. Format: 1 sentence each. If a blocker needs more than 30 seconds to explain, it goes offline to a domain-specific call — do not hold the full team.

⚠  Saturday offline meetings are MANDATORY. No exceptions except documented medical/family emergency. Whoever misses must submit a written update before 9 AM Saturday and catch up via recording.

5.  WEEK-BY-WEEK TASK BREAKDOWN

Each week has a single gate milestone. The team does not move to the next week until the gate is cleared. If behind, Saturday is used for catch-up — not the next week's tasks.

WEEK 1  (Days 1–7)  — Foundation: Set Up & First Outputs

→  Gate: PCB Gerbers sent to Lion Circuits · Tensioner assembled & installed · YOLOv8 dataset labelled (500 frames) · All 4 social handles live & 3 reels published

| Task | Owner | Due | Priority |
| --- | --- | --- | --- |
| Print tensioner saddle clamp body + lateral rod end-brackets (×2) | Skanda | Day 2 | P1 🔴 |
| Assemble and install mesh tensioner on chassis — verify no mesh slack | Hariharan + Skanda | Day 3 | P1 🔴 |
| Complete as-built SolidWorks model of v0.6 — all subassemblies | Siddiq | Day 5 | P1 🔴 |
| Run lateral slip test (without disks) — measure and record drift distance | Hariharan | Day 5 | P2 🟡 |
| Design PCB v2 in KiCad — motor ctrl, sensor stack, all power rails | Ashutosh | Day 5 | P1 🔴 |
| Submit Gerbers to Lion Circuits (specify 4-layer, 1oz copper) | Ashutosh | Day 5 | P1 🔴 |
| Bench calibrate pH, turbidity, TDS sensors vs. lab standard — document coefficients | Varshaa | Day 4 | P1 🔴 |
| Assemble 16S LiFePO₄ pack — cell matching, BMS wiring, verify OVP/UVP | Lakshya | Day 5 | P1 🔴 |
| Set up GitHub repo (private): branch strategy, README, issue templates | Adya | Day 1 | P1 🔴 |
| RPi5 dev environment: Ubuntu 22.04, Python 3.11, PyTorch, OpenCV | Adya | Day 2 | P1 🔴 |
| Define UART protocol spec (STM32↔RPi5): message format, baud rate, CRC | Adya + Ashutosh | Day 3 | P1 🔴 |
| Collect + label SCRUB lake dataset: 500+ frames (Roboflow) — 4 classes | Suraj | Day 6 | P1 🔴 |
| Implement GPS boustrophedon path planner — simulate on Kengeri polygon | Dishita | Day 6 | P2 🟡 |
| FastAPI + MQTT backend scaffold — define all data topics and endpoints | Farhan | Day 5 | P2 🟡 |
| Set up @aask.tech + @scrub.robot on IG, LinkedIn, YouTube, X, Reddit | Prasanna | Day 1 | P1 🔴 |
| Edit + post 3 reels from existing Kengeri footage (30-45s each) | Prasanna | Day 4 | P1 🔴 |
| Write + publish LinkedIn founder story post (300 words) | Prasanna | Day 3 | P2 🟡 |
| Create content calendar for 30 days in Notion — all posts planned | Prasanna | Day 5 | P2 🟡 |

✓  Week 1 Gate cleared when: Tensioner installed + PCB Gerbers sent + 500 labelled frames done + 3 reels live

WEEK 2  (Days 8–14)  — Build: Fabricate, Train, Develop

→  Gate: PCB v2 received & bench-tested · Anti-slip disks installed & drift test passed · YOLOv8 model ≥90% mAP · Dashboard live on public URL · 300 IG followers

| Task | Owner | Due | Priority |
| --- | --- | --- | --- |
| Install anti-slip disks — run lateral slip test WITH disks, record results | Hariharan + Skanda | Day 9 | P1 🔴 |
| Cut + fit fibreglass triangular side containment panels (both sides) | Skanda | Day 11 | P1 🔴 |
| Cut + install mesh liner sheet between upper/lower mesh runs | Skanda | Day 12 | P2 🟡 |
| FEA analysis of current hull (static load + buoyancy) — document safety factors | Siddiq | Day 12 | P2 🟡 |
| PCB v2 arrives from Lion Circuits — full bench test (all circuits, all rails) | Ashutosh + Varshaa | Day 10 | P1 🔴 |
| STM32 firmware: motor PWM (20 kHz), sensor ADC polling, UART TX to RPi5 | Ashutosh | Day 13 | P1 🔴 |
| Install + test 48V→12V and 48V→5V converters — verify rails under load | Lakshya | Day 10 | P2 🟡 |
| Wire harness v2: marine-grade tinned copper, colour-coded, all labelled | Varshaa | Day 13 | P2 🟡 |
| Train YOLOv8n on labelled dataset — iterate until ≥90% mAP | Suraj | Day 12 | P1 🔴 |
| Export model: confusion matrix screenshot + mAP chart + TFLite weights | Suraj | Day 13 | P1 🔴 |
| Obstacle avoidance: HC-SR04 → STM32 UART halt — bench test 3/3 pass | Dishita | Day 12 | P2 🟡 |
| Dashboard frontend: Leaflet GPS map, Chart.js sensor panels, video embed | Farhan | Day 13 | P1 🔴 |
| Deploy dashboard on public URL (Render/Railway) — share link with team | Farhan | Day 14 | P1 🔴 |
| 'Build in public' posts ×5: fabrication, PCB, sensor data, wiring progress | Prasanna | Daily | P1 🔴 |
| First Reddit post: r/robotics — 'We are building an autonomous lake-cleaning robot in Bengaluru' | Prasanna | Day 9 | P1 🔴 |
| Email United Way Bengaluru + KSPCB + Infosys Foundation (use templates) | Prasanna | Day 10 | P2 🟡 |

✓  Week 2 Gate cleared when: PCB bench-tested + model ≥90% + dashboard URL live + 300 IG followers

WEEK 3  (Days 15–21)  — Integrate: Full System on Water

→  Gate: SCRUB runs autonomously on open water for 20+ min · IP Filing 2 draft submitted to attorney · Dashboard showing live data · 1,500 IG followers · Field trial reel posted

| Task | Owner | Due | Priority |
| --- | --- | --- | --- |
| Wrap drive roller with EVA foam grip layer — re-check tensioner position | Hariharan | Day 15 | P1 🔴 |
| Propeller replacement: add screw-mount slots to CAD, print + install | Skanda | Day 17 | P1 🔴 |
| 3D print propeller guard/shroud (PETG) — install on both motor shafts | Skanda | Day 19 | P1 🔴 |
| 3 concept sketches for weed-puller mechanism — annotated pros/cons | Siddiq | Day 18 | P1 🔴 |
| Begin IP Filing 2 technical drawings (best weed-puller concept) for attorney | Siddiq + Krishna | Day 20 | P1 🔴 |
| PCB v2 conformal coating (MG Chemicals 422B) + IP65 enclosure fitting | Ashutosh | Day 16 | P1 🔴 |
| Full electronics integration into chassis — all connectors mated, tested | Ashutosh + Varshaa | Day 18 | P1 🔴 |
| GPS (NEO-M8N) installed on mast — verify NMEA stream on RPi5 | Varshaa | Day 16 | P2 🟡 |
| Install MPPT controller — test solar → battery charging cycle | Lakshya | Day 17 | P2 🟡 |
| FULL SYSTEM INTEGRATION: RPi5 + STM32 + sensors + motors — dry run | All leads | Day 18 | P1 🔴 |
| YOLOv8 deployed on RPi5 — benchmark: ≥10 FPS, CPU <80% | Suraj | Day 16 | P1 🔴 |
| End-to-end nav test: GPS waypoint → obstacle avoid → detect → collect → return | Dishita + Adya | Day 20 | P1 🔴 |
| Offline buffer: SQLite local queue + retry on reconnect — test 10-min drop | Farhan | Day 18 | P2 🟡 |
| FIELD TRIAL: Open water run — 20+ min autonomous. Record ALL data. Video shoot. | All team | Day 21 | P1 🔴 |
| Post field trial reel same day — tag BBMP, UWBe, Dr. Shanta | Prasanna | Day 21 | P1 🔴 |
| IP Filing 2 announcement post (LinkedIn + IG) — 'Second patent in development' | Prasanna | Day 20 | P2 🟡 |
| YouTube: 3-min build documentary (Week 1–3 compilation) — upload | Prasanna | Day 21 | P2 🟡 |

✓  Week 3 Gate cleared when: 20-min autonomous water run completed + reel posted + IP Filing 2 draft with attorney + 1,500 IG followers

WEEK 4  (Days 22–30)  — Polish & Launch: Demo-Ready

→  Gate: Industry-grade prototype passes 45-min unattended run · Software v1.0 released · All 3 IP filings active or submitted · 3,500 total community · Investor reel live

| Task | Owner | Due | Priority |
| --- | --- | --- | --- |
| Manufacturing BOM finalized — unit cost at 10 and 50 units verified | Siddiq + Hariharan | Day 24 | P1 🔴 |
| Prototype 2 full assembly + 45-min unattended open water run (no human touch) | All mech + elec | Day 26 | P1 🔴 |
| Write 3-page field trial report (2 runs: data, waste collected, anomalies) | Hariharan + Adya | Day 27 | P1 🔴 |
| PCB v2.1 iteration notes — document all rework wires for v3 corrections | Ashutosh | Day 24 | P2 🟡 |
| Prepare IP Filing 3 brief: PCB architecture technical drawings | Ashutosh + Krishna | Day 26 | P2 🟡 |
| GitHub: software v1.0 tag — README, API docs, install script (<30 min) | Adya | Day 24 | P1 🔴 |
| Demo mode: one-click launch, pre-loaded Kengeri waypoints, test with non-technical user | Adya + Farhan | Day 26 | P1 🔴 |
| Dashboard: Kengeri data replay mode for investor demo | Farhan | Day 25 | P2 🟡 |
| Fleet algorithm prototype: simulate 2 robots covering Kengeri polygon | Dishita | Day 27 | P3 🟢 |
| 90-second investor reel (cinematic): problem → SCRUB → data → team → ask | Prasanna | Day 27 | P1 🔴 |
| Investor pitch deck finalized + reviewed by Dr. Shanta | Prasanna + Krishna | Day 26 | P1 🔴 |
| Submit to Karnataka Elevate + DST Ignition Grant applications | Prasanna | Day 28 | P1 🔴 |
| Tweet @anandmahindra with investor reel on Day 28 | Prasanna | Day 28 | P1 🔴 |
| Demo Day event (RVCE) — invitations, logistics, live-stream setup | Prasanna | Day 30 | P1 🔴 |
| Post-Demo Day: follow-up emails to all attendees with pitch deck link | Prasanna + Krishna | Day 30 | P1 🔴 |
| DPIIT Startup India registration completed | Krishna + Prasanna | Day 24 | P1 🔴 |
| Full project report (50 pages) submitted to Dr. Shanta for certification | All leads | Day 30 | P1 🔴 |

✓  Week 4 Gate = ALL of these true on Day 30: 45-min autonomous run ✓  |  Software v1.0 ✓  |  3,500 community ✓  |  Investor reel ✓  |  Demo Day held ✓

6.  30-DAY KPI MASTER TRACKER

| KPI | Day 7 | Day 14 | Day 21 | Day 30 | Owner |
| --- | --- | --- | --- | --- | --- |
| Autonomous run duration (open water) | — | — | 20 min | 45 min | Adya / Hariharan |
| Debris detection mAP | — | ≥90% | ≥90% | ≥92% | Suraj |
| PCB version (fabricated + tested) | v2 Gerbers sent | v2 bench-tested | v2 integrated | v2.1 notes done | Ashutosh |
| IP filings active | 1 (existing) | 1 | 2 (draft with atty) | 2 submitted + 3 brief | Krishna |
| Instagram followers | 100 | 300 | 1,500 | 2,000 | Prasanna |
| LinkedIn followers | 50 | 150 | 500 | 900 | Prasanna |
| YouTube subscribers | 0 | 50 | 200 | 400 | Prasanna |
| Reddit post engagements | 0 | 50 | 200 | 500 | Prasanna |
| Email subscribers | 0 | 50 | 150 | 300 | Prasanna |
| Total community | 150 | 550 | 2,350 | 4,100 | Prasanna |
| Reels / videos published | 3 | 8 | 14 | 22 | Prasanna |
| NGO / Govt meetings confirmed | 0 | 1 | 2 | 4 | Prasanna |
| Grant applications submitted | 0 | 0 | 0 | 2 | Prasanna |
| Investor outreach sent | 0 | 0 | 2 | 10 | Prasanna |
| Field trial runs completed | 0 | 0 | 1 | 3 | Hariharan |
| Sensor suite validated vs. lab | — | Yes | Yes | Yes | Varshaa |
| Dashboard public URL live | — | Yes | Yes | Yes | Farhan |

7.  TEAM RULES — NON-NEGOTIABLE

| Rule | Detail |
| --- | --- |
| Daily commitment | Minimum 4 hours/day active work, 6 days/week. This is a full-time engagement. If you cannot commit, say so on Day 1 — not Day 10. |
| No silent disappearances | If unavailable for >2 consecutive days, inform your domain lead in advance. Silent disappearance = removed from project + no certificate. |
| Daily standup is not optional | 9 PM every day, 15 minutes. 1 sentence: done / doing / blocker. No exceptions without prior notice to Krishna. |
| Friday demos — working output only | No slides, no 'almost done'. Show working code, a printed part, a tested sensor — or explain exactly what broke and what you learned. |
| No verbal vendor instructions | All orders to 3D Printzkart, Lion Circuits, and suppliers go in writing (WhatsApp with drawing/spec attached). No verbal orders. |
| IP discipline | Nothing about the weed-puller mechanism appears publicly until IP Filing 2 is formally submitted. When in doubt — ask Krishna before posting. |
| Code quality | No undocumented function merged. Every PR has a 2-line description of what it does and how to test it. Adya reviews all merges. |
| Content approval | Prasanna submits all content to Krishna 24 hours before posting. No self-approval. Growth lead is the engine — not the decision-maker on messaging. |
| Certificate criteria | Project completion certificate issued only on delivery of ALL committed Week 4 milestones. Partial delivery = no certificate. No exceptions. |

SCRUB Team Org & Execution Plan  ·  AASK Technologies  ·  RVCE Bengaluru  ·  May 2026

Krishna Purwar — Project Lead  ·  kpurwar1234@gmail.com  ·  +91 7007633541